## Risk assessment
Risk Assessment - form to be filled out
It is important to evaluate the likelihood and severity. This is done by clicking in the relevant fields and choosing values from 1-3.
(You can click on the tab scope for further definitions of severity, probability and risk levels). The risk value is calculated automatically.
Red color in the field risk value, means the risk is unacceptable and action must be taken (see tab for action plan).
Yellow color in the field risk value, means that a risk exists and it requires consideration (see tab for action plan).
Green color in the field risk value, means the risk is minimal, and no action is required.
Date | Service - product | Person responsible
January 15. 2015 | Golden Circle | Anna Önnudóttir
Risk | Risk description | Control measures | Severity | Likelihood | Risk Value | Action
Heat or cold | Burns when stepping in to a hot spring by Geysir | Fences and warning signs | 2 | 2 | 4 | Yes
Fall | Fall or stumble on a footpath at Gullfoss | Instructions from the tour guide | 2 | 2 | 4 | Yes
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on H12: Author: If yes, move to action plan.

## Action plan
Action plan
Date | Þjónusta | Person responsible
January 15. 2015 | Golden Circle | Anna Önnudóttir
Risk after measures taken
Risk | Action taken to reduce risk | Operator | Compleation | Severity | Likelihood | Risk value
Burns when stepping in to a hot spring by Geysir | Passengers get instructions before leving the bus | AÖ | February 15. 2015 |  |  | 0
Fall at Gullfoss | Buy crampons for passengers to use in case of slippery conditions | AÖ |  |  |  | 0
0
0
0
0

## Scope
Severity | [5 empty] | Hættur |  | Dæmi
3 | Very serious | Life threatening or serious injuries with a risk of long-term disability |  |  |  | Blow |  | Collision, faling rocks
2 | fairly serious | Victim will recover from injuries sustained but requires medical attention |  |  |  | Jamed or stuck in a machine |  | Use of a heavy equipment or tools
1 | Minor | Minor injuries which cause discomfort; scratches or abrasions |  |  |  | Fall on level ground |  | Individual stumbles on a obstacles
[6 empty] | Fall from height |  | Fall in a crack, fall of a cliff
Likelihood | [5 empty] | Edged material |  | Cut
3 | Very serious | Possibility of incident high – happens often |  |  |  | Overstrain, stress |  | Sprain, collapse, heart attack
2 | fairly serious | Incident could occur – frequency low |  |  |  | Heat or cold |  | Burn, frostbite, hypotherminia
1 | Minor | Low risk of incidents – seldom happens |  |  |  | Electric shock |  | Open electrical boxes, unprotected cables
[6 empty] | Hazardous materials |  | Toxic fumes, from volcano
Key to risk assessment | [5 empty] | Drowning |  | In or near water or the see. Crossing a river
Likelihood | High | 3 | 3 | 6 | 9 | Get lost |  | To be overcome by the cold
| Medium | 2 | 2 | 4 | 6 | Infection |  | Contaminated drinking water, bathing water
| low | 1 | 1 | 2 | 3 | Nature |  | Volcanic eruptions, earthquakes
|  |  | 1 | 2 | 3 | Fire
Risk | Unacceptable |  | Low | Medium | high | Other
| Examination required |  | Severity
| Acceptable |  |  |  |  | Priorities in the handling of risk
[6 empty] | A | Avoid | Eliminate the risk by changing company operations or discontinue that part of the service which contains the risk
[6 empty] | B | Control | Make changes to decrease severity or likelihood, e.g. compose rules on work procedures and train staff
[6 empty] | C | Explain | Advertise and explain the risk by the use of markings and instructions
[6 empty] | D | Protect | Provide safety equipment and protective clothing for participants